## Read me
Synthetic project report | How to use this reference
Provenance | Synthetic tutorial fixture, not an AI-generated result or benchmark
Source | project-tasks.csv; all figures are fictional hours.
Scope | Only done tasks enter the planned-versus-actual comparison. T03 is pending with an unknown actual value.
Inputs | Blue cells in Tasks are inputs. Keep actual_hours blank when unknown. Formula cells calculate completed-work totals.
Expected checks | 8 source rows; 7 done; 1 pending; done plan 30 h; done actual 33 h; difference +3 h; all plan 32 h.
Not a product test | Generated with openpyxl, recalculated and checked mechanically. No More AI or model benchmark was run.
Reuse | CC0. Change the inputs to practise. Website version: 2026-09-14

## Tasks
task_id | project | task | status | planned_hours | actual_hours | done_variance_hours
T01 | Aurora | Research | done | 4 | 5 | 1
T02 | Aurora | Draft | done | 6 | 7 | 1
T03 | Aurora | Review | pending | 2
T04 | Boreal | Cleanup | done | 3 | 2 | -1
T05 | Boreal | Spreadsheet | done | 5 | 6 | 1
T06 | Boreal | Review | done | 2 | 2 | 0
T07 | Cedar | Interviews | done | 4 | 3 | -1
T08 | Cedar | Report | done | 6 | 8 | 2
Note on A2: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on A3: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on A4: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on A5: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on A6: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on A7: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on A8: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on A9: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on B2: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on B3: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on B4: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on B5: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on B6: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on B7: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on B8: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on B9: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on C2: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on C3: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on C4: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on C5: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on C6: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on C7: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on C8: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on C9: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on D2: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on D3: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on D4: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on D5: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on D6: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on D7: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on D8: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on D9: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on E2: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on E3: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on E4: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on E5: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on E6: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on E7: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on E8: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on E9: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on F2: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on F3: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on F4: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on F5: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on F6: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on F7: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on F8: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.
Note on F9: Source: fictional project-tasks.csv tutorial fixture, 2026-09-14. Not observed work.

## Summary
Project | Done planned h | Done actual h | Difference h | Pending tasks
Aurora | 10 | 12 | 2 | 1
Boreal | 10 | 10 | 0 | 0
Cedar | 10 | 11 | 1 | 0
Total | 30 | 33 | 3 | 1
All planned h | 32